## Sheet1
Task ID | Task Name | Duration (days) | Dependencies | Resources | Milestone | Gantt View (Simulated)
1 | Kickoff Meeting | 1 |  | Project Manager | Yes | ■
2 | Define Event Scope & Objectives | 2 | 1 | Core Team | No |  | ■ | ■
3 | Finalize Budget | 2 | 2 | Finance Lead | Yes |  |  | ■ | ■
4 | Confirm Date & Virtual Platform | 2 | 2 | Tech Lead | Yes |  |  |  | ■ | ■
5 | Design Event Branding & Assets | 3 | 3 | Design Interns | No |  |  |  |  | ■ | ■ | ■
6 | Invite and Confirm Speakers | 5 | 2 | Speaker Liaison | Yes | [5 empty] | ■ | ■ | ■ | ■ | ■
7 | Build Agenda | 3 | 6 | Program Coordinator | Yes | [6 empty] | ■ | ■ | ■
8 | Set Up Registration Page | 2 | 4,5 | Tech Interns | Yes | [7 empty] | ■ | ■
9 | Promote Event | 7 | 8 | Marketing Team | Yes | [8 empty] | ■ | ■ | ■ | ■ | ■ | ■ | ■
10 | Conduct Technical Rehearsal | 1 | 6,4 | Tech Team, Speakers | Yes | [9 empty] | ■
11 | Event Day Execution | 1 | 10 | All Teams | Yes | [10 empty] | ■
12 | Post-Event Survey & Wrap-up | 2 | 11 | Program & Marketing Team | Yes | [11 empty] | ■ | ■